## Resource Optimised
Days | Start time | Task | Type | People | Time | Width
0 | 0 | Create design ticket | Required waste | 1 | 0.1 | 1.875
0.0125 | 0.1 | Design work | Value add | 2 | 16 | 300
2.0125 | 16.1 | Wait for design meeting | Queue | 0 | 16 | 300
4.0125 | 32.1 | Design meeting | Value add | 15 | 1 | 18.75
4.1375 | 33.1 | Close design ticket | Required waste | 1 | 0.1 | 1.875
4.15 | 33.2 | Create analysis ticket | Required waste | 1 | 0.1 | 1.875
4.1625 | 33.3 | Wait for analysis work | Queue | 0 | 20 | 375
6.6625 | 53.3 | Analysis work | Value add | 2 | 4 | 75
7.1625 | 57.3 | Close analysis ticket | Required waste | 1 | 0.1 | 1.875
7.175 | 57.4 | Create development ticket | Required waste | 1 | 0.3 | 5.625
7.2125 | 57.7 | Prioritize development ticket | Value add | 1 | 1 | 18.75
7.3375 | 58.7 | Wait for PBR | Queue | 0 | 16 | 300
9.3375 | 74.7 | PBR | Value add | 21 | 1 | 18.75
9.4625 | 75.7 | Prepare sprint planning materials | Required waste | 1 | 3 | 56.25
9.8375 | 78.7 | Sprint planning | Value add | 20 | 1.7 | 31.875
10.05 | 80.4 | Development backlog | Queue | 0 | 40 | 750
15.05 | 120.4 | Scrum of scrums | Required waste | 5 | 1 | 18.75
15.175 | 121.4 | Tech debt review meeting | Required waste | 20 | 1 | 18.75
15.3 | 122.4 | Retrospective | Required waste | 20 | 1 | 18.75
15.425 | 123.4 | Stand up | Required waste | 20 | 0.5 | 9.375
15.4875 | 123.9 | Daily automation call | Required waste | 2 | 0.3 | 5.625
15.525 | 124.2 | Wait for refinement | Queue | 0 | 20 | 375
18.025 | 144.2 | Refine requirements | Value add | 2 | 1 | 18.75
18.15 | 145.2 | Coding (implementation) | Value add | 1 | 8 | 150
19.15 | 153.2 | Wait for BA | Queue | 0 | 8 | 150
20.15 | 161.2 | Wait for code review | Queue | 0 | 8 | 150
21.15 | 169.2 | Cruicible code review | Value add | 4 | 0.3 | 5.625
21.1875 | 169.5 | Coding (review feedback) | Value add | 1 | 2 | 37.5
21.4375 | 171.5 | Create release package for QA Eng | Value add | 1 | 0.2 | 3.75
21.4625 | 171.7 | Wait for release package to build | Queue | 0 | 2 | 37.5
21.7125 | 173.7 | Deploy to QA Eng | Value add | 1 | 0.5 | 9.375
21.775 | 174.2 | Wait for QA team | Queue |  | 4 | 75
22.275 | 178.2 | QA test and sign off | Value add | 1 | 5 | 93.75
22.9 | 183.2 | Add QA defect to dev ticket | Required waste | 2 | 0.2 | 3.75
22.925 | 183.4 | Coding (fix QA defect) | Value add | 1 | 4 | 75
23.425 | 187.4 | Wait for sprint review demo | Queue | 0 | 40 | 750
28.425 | 227.4 | Sprint review demo | Value add | 20 | 1 | 18.75
28.55 | 228.4 | Wait for release | Queue | 0 | 80 | 1500
38.55 | 308.4 | Branch for release | Required waste | 2 | 0.2 | 3.75
38.575 | 308.6 | Review check-ins | Required waste | 2 | 2 | 37.5
38.825 | 310.6 | Wait for integration | Queue | 0 | 8 | 150
39.825 | 318.6 | Integration | Required waste | 1 | 3 | 56.25
40.2 | 321.6 | Create release package for regression | Value add | 1 | 0.2 | 3.75
40.225 | 321.8 | Wait for regression test | Queue | 0 | 1 | 18.75
40.35 | 322.8 | QA regression test | Value add | 6 | 4 | 75
40.85 | 326.8 | Create Regression ticket | Required waste | 1 | 0.2 | 3.75
40.875 | 327 | Coding (fix regression defect) | Required waste | 1 | 8 | 150
41.875 | 335 | Close Regression ticket | Required waste | 1 | 0.2 | 3.75
41.9 | 335.2 | Change paperwork (SNOW, QA ticket) | Required waste | 3 | 0.5 | 9.375
41.9625 | 335.7 | Chasing sign offs | Required waste | 1 | 0.5 | 9.375
42.025 | 336.2 | Create release run book | Value add | 1 | 0.5 | 9.375
42.0875 | 336.7 | Release run book review | Value add | 5 | 1 | 18.75
42.2125 | 337.7 | CAB | Required waste | 3 | 0.3 | 5.625
42.25 | 338 | Wait for release window | Queue | 0 | 16 | 300
44.25 | 354 | Application release | Value add | 2 | 2 | 37.5
[5 empty] | 356 | 44.5
|  |  | Value add |  | 54.4 | 6.8
|  |  | Required waste |  | 22.6 | 2.825
15.28%

## Flow Optimised
Days | Start time | Task | Type | People | Time | Width
0 | 0 | Create story ticket | Required waste | 1 | 0.1 | 1.875
0.0125 | 0.1 | Research and analysis | Value add | 1 | 4 | 75
0.5125 | 4.1 | Draft specification | Value add | 1 | 2 | 37.5
0.7625 | 6.1 | Wait for specification workshop | Queue | 0 | 4 | 75
1.2625 | 10.1 | Specification workshop | Value add | 4 | 1 | 18.75
1.3875 | 11.1 | Specification linked to story | Required waste | 1 | 0.1 | 1.875
1.4 | 11.2 | PO authorises story ticket | Required waste | 1 | 0.1 | 1.875
1.4125 | 11.3 | Design work | Value add | 2 | 8 | 150
2.4125 | 19.3 | Automate specification checks | Value add | 2 | 8 | 150
3.4125 | 27.3 | Code and automated tests | Value add | 4 | 8 | 150
4.4125 | 35.3 | Wait for build pipeline | Queue | 0 | 1 | 18.75
4.5375 | 36.3 | Wait for QA | Queue | 0 | 1 | 18.75
4.6625 | 37.3 | Exploratory testing | Value add | 1 | 1 | 18.75
4.7875 | 38.3 | QA sign off | Required waste | 1 | 0.1 | 1.875
4.8 | 38.4 | Wait for application release | Queue | 0 | 1.4 | 26.25
4.975 | 39.8 | Application release | Value add | 1 | 0.1 | 1.875
4.9875 | 39.9 | Close story ticket | Required waste | 1 | 0.1 | 1.875
[5 empty] | 40 | 5
|  |  | Value add |  | 32.1 | 4.0125
|  |  | Required waste |  | 0.5 | 0.0625
80.25%